## Tabelle1
Time Spent | 73
Date | Duration in h | Task
08.12.2025 | 3 | Write Design Document (Miro Board)
14.01.2026 | 1 | Project Setup with 3rd Person Template
14.01.2026 | 2 | Changing Camera from 3rd Person to a static angled Top-Down Camera
14.01.2026 | 1 | Changed Movement form 3rd Person to Twin Stick (only left stick)
14.01.2026 | 3 | Adding Local Multiplayer (with one Static Camera)
15.01.2026 | 1 | Added a new Player Character Asset
15.01.2026 | 4 | Implemeted Character Rotation (Right Stick)
15.01.2026 | 6 | Added Shooting (rebuilt the full Project with First Person Shooter Template)
16.01.2026 | 1.5 | Shooting for Mutliplayer
16.01.2026 | 3 | Health UI (also removed unused UI from Template)
16.01.2026 | 1 | Implemeted Weapon and Bullet (Copy from Template with some small collision, physics and Damage changes)
16.01.2026 | 0.5 | Updated Game Design Document
17.01.2026 | 2 | Bullet Collision, Bouncing and Despawning logic (max TTL, max Bounces)
17.01.2026 | 1.5 | Tried to fix Template Animations for new Player Character Asset
17.01.2026 | 0.5 | Set Bullet Color per Player Color
17.01.2026 | 0.5 | Create Damage Types for each Player Color (Own Color -> Heal, Other Color -> Damage)
17.01.2026 | 0.5 | Improved Aiming with forward pointing Laser
17.01.2026 | 1 | Added Logic for Player Score Calcualtion + UI
17.01.2026 | 0.5 | Default Player Weapon (Removed Template Weapon Pickup Logic)
17.01.2026 | 2 | Added Player Respawning upon Death
17.01.2026 | 6.5 | Build the "Outpost" Level
18.01.2026 | 2.5 | Added Game Timer
18.01.2026 | 1 | Updated Event Handling for the full Project
18.01.2026 | 1 | Added a Lobby UI ("Waiting for Players…")
18.01.2026 | 1 | Added VFX to the Bullets
18.01.2026 | 0.5 | Searched for Sound Effect Libraries
18.01.2026 | 3.5 | Added Background Music and Sound Effects (Player, Weapon and Bullets)
18.01.2026 | 0.5 | Fixed Sounds and Camera when Game starts paused
18.01.2026 | 1 | Added a Winner Screen ("XXX Player has Won")
18.01.2026 | 1 | Added Logic for "Play Again" Button
18.01.2026 | 1 | Added Controller Support for the UI
19.01.2026 | 0.5 | Plan open ToDos
19.01.2026 | 2 | Added Countdown befor Match Start
19.01.2026 | 0.5 | Tried to fix UI Warning (Widget already in Viewport )
19.01.2026 | 0.5 | Fixed Bug where Controlls where disabled after UI closed
19.01.2026 | 0.5 | Added "Exit Game" Button to Win Screen
19.01.2026 | 2.5 | Implemented UI Wraper to change Color of Focused Element and play Sound Effects on Focus changed (Why is this not natively implemented in unreal)
19.01.2026 | 0.5 | Handle Draw (2-3 Players with equal Scores)
19.01.2026 | 1.5 | Added a Slider to set the Match Duration
20.01.2026 | 0.5 | Plan open ToDos
20.01.2026 | 1 | Add UI Sounds
20.01.2026 | 0.5 | Added Sound Effects to Match End (Winner or Draw)
20.01.2026 | 2.5 | Added a Pause/Setting Menu with Sound Sliders
20.01.2026 | 0.5 | Handle Bullets that hit dead Player Ragdolls
20.01.2026 | 1 | Tried to fix Template Animations for new Player Character Asset again
20.01.2026 | 1 | Created Git Repo and Migrated Game to a Blank Project
20.01.2026 | 1 | Building an Executeable for Windows
20.01.2026 | 0.5 | Fix Bug with Exit Game Button
20.01.2026 | 1 | Updating Documentation + Hand In